## project WBS monitor
project: | WorkBreakdown Structure (WBS) monitor |  |  | remark | WBS id is reference to chapter in functional design (FD)
calculator: |  |  |  | remark | for FD: chapter are not chronological
date: | 2015-10-16 |  |  | do not | change the WBS id number for a task
WBS id | predecessor | task | requirement level (MoSCoW) | developer | Risc | duration, min (plan) | duration, min (do) | evaluation (check) | action (act)
1 |  | Vendors | M | [ Jordy ] |  | 5 | 10
2 |  | Interactable Objects | M | [ Jordy ] |  | 5 | 15
3 |  | Food/Water System | M | [ Jordy ] |  | - | -
4 |  | Killable Players [Health] | M | [ Jordy ] |  | - | -
5 |  | Wapens | M | [ Jordy ] |  | - | -
6 |  | Boten / Boat Spawning | M | [ Jordy ] |  | 10 | 60
7 |  | Wapen Uit/Aan | M | [ Jordy ] |  | 10 | 60
8 |  | Boot Besturen Met Arduino | M | [ Nordin ] |  | 10 | 130
9 |  | Eilanden Om te vinden | M | [ Nordin ] |  | 5 | 30
10 |  | Zwemmen | M | [ Nordin ] |  | 5 | 20
11 |  | Flag Capture | M | [ Jordy ]
12 |  | Villages | M | [ Nordin ] |  | 5 | 30
13 |  | Extra Arduino Features | M | [ Nordin ] |  | 10 | 150
14 |  | Schatkisten | S | [ Jordy ] |  | 15 | 60
15 |  | Huizen Kopen | S | [ Jordy ] |  | 10 | 40
16 |  | Arduino Movement verbeteren | S | [ Nordin ] |  | 10 | 120
17 |  | Camera Via Arduino | S | [ Nordin ] |  | 5 | 90
18
19
|  | total |  |  |  | 0 | 10

## MoSCoW
M | MUST | Describes a requirement that must be satisfied in the final solution for the solution to be considered a success.
S | SHOULD | Represents a high-priority item that should be included in the solution if it is possible. This is often a critical requirement but one which can be satisfied in other ways if strictly necessary.
C | COULD | Describes a requirement which is considered desirable but not necessary. This will be included if time and resources permit.
W | WON'T | Represents a requirement that stakeholders have agreed will not be implemented in a given release, but may be considered for the future. (note: occasionally the word "Would" is substituted for "Won't" to give a clearer understanding of this choice).

## version
datum | door | versieomschrijving
2015-10-09 | kadi | originele basisversie aangepast aan ideeën van Six Sigma